## Tracker
Row ID | Project | SKU / Variant | APIs | Strengths | Dosage Form | Initial Intake | APIs to Pete Pharma | Formula Development | Samples to Curexa | Sample Feedback | Formula Finalized | SOP Finalized | Production | Progress | Last Updated | Updated By
R001 | Topical Estriol Cream Formula Optimization (Anhydrous) | — | Estriol | — | Topical Anhydrous | Completed | N/A | Completed | Completed | In Progress | Completed | Completed | Not Started | 71.43% | 2026-10-03 | Migration
R002 | Bimatoprost Eye Serum (Anhydrous) | — | Bimatoprost | 0.035% | Topical Anhydrous | Completed | Completed | Completed | Completed | In Progress | Completed | Completed | Not Started | 75% | 2026-10-03 | Migration
R003 | GHK-Cu Topical Hair Solution (Anhydrous) | — | GHK-Cu | 4% | Topical Anhydrous | Completed | Completed | In Progress | Completed | Completed | Completed | Completed | Not Started | 75% | 2026-10-03 | Migration
R004 | Cardiovascular Oral Tablets | SKU 1 | Atorvastatin; CoQ10; Resveratrol; Pyridoxine HCl | 11.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | 62.5% | 2026-10-03 | Migration
R005 | Cardiovascular Oral Tablets | SKU 2 | Atorvastatin; CoQ10; Resveratrol; Pyridoxine HCl | 23 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | 62.5% | 2026-10-03 | Migration
R006 | Cardiovascular Oral Tablets | SKU 3 | Atorvastatin; Ezetimibe; CoQ10; Resveratrol; Pyridoxine HCl | 11.5 mg; 8.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | 50% | 2026-10-03 | Migration
R007 | Cardiovascular Oral Tablets | SKU 4 | Atorvastatin; Ezetimibe; CoQ10; Resveratrol; Pyridoxine HCl | 23 mg; 8.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Completed | Completed | Completed | Not Started | Not Started | Not Started | Not Started | 50% | 2026-10-03 | Migration
R008 | Cardiovascular Oral Tablets | SKU 5 | Rosuvastatin; CoQ10; Resveratrol; Pyridoxine HCl | 5.6 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Blocked | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | 25% | 2026-10-03 | Migration
R009 | Cardiovascular Oral Tablets | SKU 6 | Rosuvastatin; CoQ10; Resveratrol; Pyridoxine HCl | 11.2 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Blocked | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | 25% | 2026-10-03 | Migration
R010 | Cardiovascular Oral Tablets | SKU 7 | Rosuvastatin; Ezetimibe; CoQ10; Resveratrol; Pyridoxine HCl | 5.6 mg; 8.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Blocked | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | 25% | 2026-10-03 | Migration
R011 | Cardiovascular Oral Tablets | SKU 8 | Rosuvastatin; Ezetimibe; CoQ10; Resveratrol; Pyridoxine HCl | 11.2 mg; 8.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Blocked | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | 25% | 2026-10-03 | Migration
R012 | Cardiovascular Oral Tablets | Sample run (200 tabs) | Atorvastatin; Rosuvastatin; Ezetimibe; CoQ10; Resveratrol; Pyridoxine HCl | 23 mg; 11.2 mg; 8.5 mg; 100 mg; 100 mg; 2.44 mg | Oral IR Tablet | Completed | Blocked | Completed | Not Started | Not Started | Not Started | Not Started | Not Started | 25% | 2026-10-03 | Migration
R013 | Sermorelin Tablets | 1000 mcg | Sermorelin | 1000 mcg | ODT | Completed | Completed | Completed | Completed | Completed | Completed | Completed | In Progress | 87.5% | 2026-10-03 | Migration
R014 | Sermorelin Tablets | 500 mcg | Sermorelin | 500 mcg | ODT | Completed | Completed | Completed | Completed | Completed | Completed | Completed | In Progress | 87.5% | 2026-10-03 | Migration
R015 | Topical GHK-Cu Anhydrous Cream | — | GHK-Cu | 2% | Versapro Anhydrous Topical | Completed | In Progress | In Progress | Completed | Completed | Completed | Completed | Not Started | 62.5% | 2026-10-03 | Migration
R016 | Sildenafil/Tadalafil Combo ODT | 56/12 mg — White | Sildenafil; Tadalafil | 56 mg; 12 mg | ODT | Completed | Completed | In Progress | Completed | Completed | Completed | Completed | Not Started | 75% | 2026-10-03 | Migration
R017 | Sildenafil/Tadalafil Combo ODT | 84/17 mg — White/Blue Specks | Sildenafil; Tadalafil | 84 mg; 17 mg | ODT | Completed | Completed | In Progress | Completed | Completed | Completed | Completed | Not Started | 75% | 2026-10-03 | Migration
R018 | Sildenafil/Tadalafil Combo ODT | 110/23 mg — Pale Blue | Sildenafil; Tadalafil | 110 mg; 23 mg | ODT | Completed | Completed | In Progress | Completed | Completed | Completed | Completed | Not Started | 75% | 2026-10-03 | Migration
R019 | NAD+/Glutathione/Methyl B12 ODT | — | NAD+; Glutathione; Methylcobalamin (B12) | 150 mg; 50 mg; 1 mg | ODT | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Started | 87.5% | 2026-10-03 | Migration
R020 | Anhydrous Nasal Spray | — | TBD | TBD | Anhydrous Nasal Spray | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 0% | 2026-10-03 | Migration
R021 | Pre-Workout Powder Sachets | Daily Performance | Tadalafil; Creatine Monohydrate; L-Citrulline; Taurine | 5 mg; 5 g; 3 g; 1.5 g | Powder for Oral Solution (Sachet) | Completed | In Progress | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | 12.5% | 2026-10-03 | Migration
R022 | Pre-Workout Powder Sachets | PRN Pre-Workout | Sildenafil; L-Citrulline; Beta-Alanine; Taurine; Caffeine; L-Theanine; L-Tyrosine; Na/K/Mg | 25 mg; 5 g; 1.6 g; 1.5 g; 200 mg; 100 mg; 500 mg; 350/200/50 mg | Powder for Oral Solution (Sachet) | Completed | In Progress | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | 12.5% | 2026-10-03 | Migration

## Notes
Date | Project | SKU / Variant | Author | Note
2026-10-03 | Migration | — | Claude (migration) | Workbook restructured from original tracker: one row per SKU, standardized statuses (Not Started / In Progress / Blocked / Completed / N/A). Original nuance captured in the notes below.
2026-10-03 | Cardiovascular Oral Tablets | SKU 5–8 + sample run | Migration | 'APIs to Pete Pharma' marked Blocked — awaiting Rosuvastatin.
2026-10-03 | GHK-Cu Topical Hair Solution (Anhydrous) | — | Migration | Formula Development status was 'Re-evaluation in Progress'. Production noted as TBD.
2026-10-03 | Topical GHK-Cu Anhydrous Cream | — | Migration | Target: periwinkle color; mask unpleasant odor. Open question from Curexa: 'How much GHK-Cu is remaining? We are working hard to find another vendor.'
2026-10-03 | Sildenafil/Tadalafil Combo ODT | All SKUs | Migration | 25 samples of each SKU. Formula Development status was 'Re-evaluation in Progress'.
2026-10-03 | Topical Estriol Cream Formula Optimization (Anhydrous) | — | Migration | 'Samples to Curexa' was recorded as 'Pete Pharma Sample Completed'.
2026-10-03 | Bimatoprost Eye Serum (Anhydrous) | — | Migration | 'Samples to Curexa' was recorded as 'Pete Pharma Sample Completed'.
2026-10-03 | Anhydrous Nasal Spray | — | Migration | Early intake. Open items: Curexa to send ingredient list + absorption data; must cross blood-brain barrier; ensure scalability; evaluate propanediol as base.
2026-10-03 | Pre-Workout Powder Sachets | Both SKUs | Migration | Added from current formulation work: Curexa sending APIs for 10-sachet sample runs of each product. Formulation proposals drafted.

## ReadMe
Pete Pharma x Curexa — R&D Project Tracker (v2)
How this workbook works
• One row per SKU/variant on the Tracker sheet. The portal website reads and writes this file via Microsoft Graph.
• Stage columns (G–N) use a dropdown: Not Started / In Progress / Blocked / Completed / N/A. Please use only these values — the website relies on them.
• The Progress column is a formula (Completed stages ÷ applicable stages). Don't overwrite it.
• Detail and discussion go on the Notes sheet (newest at the bottom). The website appends notes there too.
• You can edit this file directly in Excel at any time — just keep the table structure: don't rename sheets, tables, or column headers.
Editable cells
• Tracker: columns B–F (project info) and G–N (stage statuses via dropdown).
• Notes: add rows at the bottom of the table.
• Row ID (column A) must stay unique — next available is R023.
Example row format
• R023 ¦ "New Project Name" ¦ "SKU 1" ¦ "API A; API B" ¦ "10 mg; 20 mg" ¦ "ODT" ¦ stage columns via dropdown.
Status legend
• Completed (green) — stage done
• In Progress (yellow) — actively being worked
• Blocked (red) — waiting on material/info (see Notes)
• Not Started (gray) — not yet begun
• N/A — stage doesn't apply to this project
Migrated 2026-10-03 from the original tracker. Original status nuances preserved on the Notes sheet.